## R&R
Activity	Work Product	Customer	Sponsor	Project / Director	PM	TL	Developer	Tester	CC
Develop project plan	Project Plan	I	I	A	D	R	I	I	I
Develop CM plan	CM Plan		I		A	R	R	R	D
Conduct weekly project report	Weekly report	I			D	R
Create user requirement	URD	D/A	R	R	A
Create software requirements specification	SRS	A	R		A	D	I	I
Develop prototype	Prototype	A	I	I	A	D	D	R
Create architectural design document	ADD	R		R	A	D	R	R
Create detail design document	DDD				A	D	D	I
Code module	Software module				I	R/A	D	I
Unit Test					I	A	D	R
Integrate module					I	D/A	D	R
Design test and prepare test data						A	R	D
Conduct integration test					I	D/A	D	I
Conduct system test					A	R		D
Deliver software to customer		I	I	I	D	I	I	R
Fix bugs in acceptance					A	D	D	R
Create installation manual					A	D	I	R
Create user manual					A	D	I	R

Notes: D – Do; R – Review; I - Informed; A – Accept

## Stages
Stage	Activity	Input	Work Product	Customer	Sponsor	Project / Director	PM	TL	Developer	Tester	CC
Initiation
Initiation
Initiation
Initiation
Initiation
Initiation
Initiation
Definition
Definition
Definition
Definition
Definition
Definition
Definition
Definition
Definition
Solution
Solution
Solution
Solution
Solution
Solution
Solution
Construction
Construction
Construction
Construction
Construction
Construction
Construction
Transition
Transition
Transition
Transition
Transition
Termination
Termination